## Sheet1
Day | Date | Agenda | Participants
Day1 | 2019-03-11 | Kick-off meeting for AMI(Automated Metering Infrastructure) Ohio, PSO and APCO remediation projects | Ravikant Beera, Sandeep Bhannori,Robin F Lesher,Neil M Rider
Day 2 to Day 5 | 04/12/2019 to 03/15/2019 | Meeting with project SMEs(subject matter experts) for requirement gathering of AMI Ohio module. Meeting with BU (business user) to understand the business functionality of AMI Ohio module. Meeting with SMEs(subject matter experts) to understand the architecure of AMI Ohio module and taking hand over of module from SME. | Ravikant Beera, Sandeep Bhannori,,Sudheesh Vasudevan,Michale Berlan,Meeta Kathuria,Terryl L Mooney
Day 6 to Day 9 | 03/18/2019 to 03/21/2019 | Meeting with project SMEs(subject matter experts) for requirement gathering of AMI PSO module. Meeting with BU (business user) to understand the business functionality of AMI PSO module. Meeting with SMEs(subject matter experts) to understand the architecure of AMI PSO module and taking hand over of module from SME. | Ravikant Beera, Sandeep Bhannori,,Sudheesh Vasudevan,Michale Berlan,Meeta Kathuria,Terryl L Mooney
Day 10 to Day 13 | 3/22/2019 to 03/27/2019 | Meeting with project SMEs(subject matter experts) for requirement gathering of AMI APCO module. Meeting with BU (business user) to understand the business functionality of AMI APCO module. Meeting with SMEs(subject matter experts) to understand the architecure of AMI APCO module and taking hand over of module from SME. | Ravikant Beera, Sandeep Bhannori,,Sudheesh Vasudevan,Michale Berlan,Meeta Kathuria,Terryl L Mooney
Day 14 | 2019-03-28 | Meeting with DBA team and understand the schema architecture of all AMI modules | Michale Berlan, Adibabu Jampani
Day 15 | 2019-03-29 | Give PPT presentation to AEP team on ITMP (Infrastructure Technology Remediation Program) running applications and scope of Cloud Computing in ITMP. Give PPT presentation to AEP team on the effective use of DevOps like Jenkins during ITMP remediation. | Ravikant Beera, Sandeep Bhannori,Robin F Lesher,Neil M Rider,Meeta Kathuria